## marmalade__20141217_1204.csv
Title | Labels | Iteration | Type | Estimate | Current State | Created at | Accepted at | Requested By | Description | URL | Owned By
Researching Phonegap | application, frontend, research, setting up the front-end | 1 | feature | 2 | accepted | Sep 26, 2014 | Oct 10, 2014 | Flutra Tahiraj | Research up on their generator and policy, copyrights | https://www.pivotaltracker.com/story/show/79635234 | Palina Kolos
Set up Server | frontend, server | 3 | feature | 2 | accepted | Sep 26, 2014 | Oct 24, 2014 | Flutra Tahiraj | Create/"borrow" server. sprint for F.T + M.W) Riak cant work on the chalmer server that we had. So we are going to get a server from Jani that we can use for this term/project. | https://www.pivotaltracker.com/story/show/79636484 | Flutra Tahiraj
Researching Twitter API | backend, research, setting up the backend | 4 | feature | 2 | accepted | Sep 22, 2014 | Nov 2, 2014 | Fredric Eidsvik | researching, module, connect to twitter API | https://www.pivotaltracker.com/story/show/79259910 | David M Szabo
Researching "Hello World" | helloworld, research | 4 | feature | 1 | accepted | Sep 26, 2014 | Nov 2, 2014 | Flutra Tahiraj | Understand the skeleton and the modules, etc | https://www.pivotaltracker.com/story/show/79635586
Researching Riak | research, riak, setting up the backend | 5 | feature | 1 | accepted | Sep 26, 2014 | Nov 7, 2014 | Flutra Tahiraj | Research, riak | https://www.pivotaltracker.com/story/show/79635438 | Markus Erlach
Researching Riak | research, setting up the backend | 10 | feature | 1 | accepted | Sep 26, 2014 | Dec 8, 2014 | Alexander Ask | Learn Riak on Linux | https://www.pivotaltracker.com/story/show/79581804 | David Lindenberg
Researching Server | frontend, research, setting up the front-end | 10 | feature | 1 | accepted | Sep 26, 2014 | Dec 8, 2014 | Flutra Tahiraj | Research server, | https://www.pivotaltracker.com/story/show/79635290 | Flutra Tahiraj
Researching Riak | research, riak, setting up the backend | 10 | feature | 1 | accepted | Sep 26, 2014 | Dec 8, 2014 | Flutra Tahiraj | Research on Mac | https://www.pivotaltracker.com/story/show/79635386 | mengjiao wei
Getting Ubuntu to work on a preinstalled windows 8 |  | 10 | feature | 1 | accepted | Oct 10, 2014 | Dec 8, 2014 | Fredric Eidsvik |  | https://www.pivotaltracker.com/story/show/80439122 | Fredric Eidsvik
Transformer | setting up the backend | 10 | feature | 2 | accepted | Oct 24, 2014 | Dec 8, 2014 | Fredric Eidsvik | Transformer will be done by David Lindenberg and Fredric Eidsvik | https://www.pivotaltracker.com/story/show/81358262 | Fredric Eidsvik
Quering DB -Erl | data, database, query, setting up the backend | 11 | feature | 2 | accepted | Oct 6, 2014 | Dec 17, 2014 | Flutra Tahiraj | Querying database in Erlang (sprint for D.L + M.E) | https://www.pivotaltracker.com/story/show/80151142 | Flutra Tahiraj
Documentation | doc. | 11 | feature | 1 | accepted | Oct 6, 2014 | Dec 17, 2014 | Flutra Tahiraj | Start the documentation | https://www.pivotaltracker.com/story/show/80152182 | Flutra Tahiraj
Loader | backend, database, setting up the backend, twitter | 11 | feature | 2 | accepted | Oct 24, 2014 | Dec 17, 2014 | Flutra Tahiraj | Loader is up to Mengjiao Wei and Flutra | https://www.pivotaltracker.com/story/show/81358158 | mengjiao wei
Webhost/domain & Website |  | 11 | feature | 2 | accepted | Nov 7, 2014 | Dec 17, 2014 | Fredric Eidsvik | Getting the domain, webhost and website to work. | https://www.pivotaltracker.com/story/show/82271648 | David M Szabo
Changeing the level of the database. |  | 11 | feature | 10 | accepted | Nov 25, 2014 | Dec 17, 2014 | Markus Erlach | We need to change the lvl of data base to LevelDB for secundary indexing. getting the map recduce to work with our online server mapreduce to server. | https://www.pivotaltracker.com/story/show/83381950 | Fredric Eidsvik
Language and location |  | 11 | feature | 5 | accepted | Nov 25, 2014 | Dec 17, 2014 | Fredric Eidsvik | Try some more if we are able to get swedish tweets, otherwise get english. | https://www.pivotaltracker.com/story/show/83382142 | Fredric Eidsvik
Webpage |  | 11 | feature | 10 | accepted | Nov 25, 2014 | Dec 17, 2014 | Flutra Tahiraj | show on the webpage so we can start working on the top ‪#‎list‬. and hoppflully get location on the map. / start with dummy data. | https://www.pivotaltracker.com/story/show/83382110 | Fredric Eidsvik
Riak, erlang and PHP |  | 11 | feature | 10 | accepted | Nov 25, 2014 | Dec 17, 2014 | Fredric Eidsvik | Change backend of riak server. fix connection to real server. connect the query handler to php to send data. | https://www.pivotaltracker.com/story/show/83382022 | Fredric Eidsvik
Building the extractor | query, setting up the backend, twitter | 11 | feature | 3 | accepted | Oct 24, 2014 | Dec 17, 2014 | Markus Erlach | Extractor. David D & Markus is doing the extractor | https://www.pivotaltracker.com/story/show/81358082 | David M Szabo